## LVC
S.no | Area | Task | Status | Ownership | Comments
1 | Catalog | Category Structure | Pending | LVC team | product data pending
2 |  | Products | Pending | LVC team | product data pending
3 |  | inventory | Pending | LVC team | product data pending
4 |  | prices | Pending | LVC team | product data pending
5 |  | Images | Pending | LVC team | product data pending
6 |  | Delivery charges | Pending | LVC team | product data pending
7 |  | Tax Charges | Pending | LVC team | product data pending
8 |  | Service Charges | Pending | LVC team | product data pending
| Design | Logo | Pending | Ravi /Srini | Will share the WP themes
9 |  | Home page | WIP | NetN | Will share the WP themes
10 |  | Home Page teasers | WIP | NetN | Will share the WP themes
11 |  | Category Page | WIP | NetN | Will share the WP themes
12 |  | Product Detail Page | WIP | NetN | Will share the WP themes
13 |  | Quick view | WIP | NetN | Will share the WP themes
| Checkout | Customer Login | Pending | NetN | Setup to be initiated
14 |  | Guest User Login | Pending | NetN | Setup to be initiated
15 |  | Billing Address | Pending | NetN | Setup to be initiated
16 |  | Shipping Address | Pending | NetN | Setup to be initiated
17 |  | Payment options | Pending | NetN | Setup to be initiated
20 |  | Pay on delivery | Pending | NetN | Setup to be initiated
21` |  | Authorize.net online PG setup | Pending | LVC team | Setup to be initiated
Consumer Journey
22 |  | Login to website | Pending | NetN | Will share the WP themes
23 |  | Registrations | Pending | NetN | Will share the WP themes
24 |  | Browse through all categories | Pending | NetN | Will share the WP themes
25 |  | Browse through all products | Pending | NetN | Will share the WP themes
26 |  | Price Filter | Pending | NetN | Will share the WP themes
27 |  | Saved Cart | Pending | NetN | Will share the WP themes
28 |  | Wish List | Pending | NetN | Will share the WP themes
29 |  | My Account | Pending | NetN | Will share the WP themes
30 |  | Saved orders | Pending | NetN | Will share the WP themes
31 |  | Re order | Pending | NetN | Will share the WP themes
|  | Search page setup | Pending | NetN | Will share the WP themes
|  | Best Seller Showcase Setup | Pending | NetN | Will share the WP themes
|  | Newsletter | Pending | NetN | Will share the WP themes
31 | OMS | Order review | Pending | NetN | Setup to be initiated
32 |  | Order process | Pending | NetN | Setup to be initiated
33 |  | order cancellation | Pending | NetN | Setup to be initiated
34 |  | order dispatch / dleivery | Pending | NetN | Setup to be initiated
35 |  | failed order management | Pending | NetN | Setup to be initiated
37 |  | Pending order management | Pending | NetN | Setup to be initiated
| Customer Help | Live chat setup | Pending | NetN | Setup to be initiated
38 |  | Social page setup | Pending | NetN | Setup to be initiated
39 |  |  | Pending | NetN | Setup to be initiated
40 | Domain | Domain name procurement | Pending | LVC team | Setup to be initiated
50 | Hostin | Hosting space to be initated | Pending | LVC team | Setup to be initiated